## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  |  | Null values in loan_amount column not handled | Sprint 1 | Backend Team | Logical | Added null-handling logic |  | closed | All records now handled
2 |  |  | Incorrect encoding of categorical gender field | Sprint 2 | DS Team | Standards | Corrected encoding function |  | closed | Compliance with data standards
3 |  |  | Features mismatch between training and prediction input | Sprint 3 | DS Team | Maintainability | Synchronized feature lists |  | closed | Better code maintainability
4 |  |  | No input validation on Streamlit income fields | Sprint 3 | Frontend Team | User Interface | Added type & value validation |  | closed | Improved UX
5 |  |  | Flask API crashes on special characters in email signup | Sprint 4 | Backend Team | Logical | Implemented regex validation |  | closed | Prevented crashes

## Sheet2
Logical
User Interface
Maintainability
Standards
Others